## RoadMap
Services | Sub Category | Core Product/Service | Scource | Client | Requirements | Delivery | Responsible Person | Implementation (3 Months Duration) | Required Resources | Designation | Start Time | End Time
Intranet Services | Web Services | Internet Access | In-House | BBCWSTBD |  | Development of E-mail site New Content upload, Registration information | Mr. Shahab | Domain Name registration Information
[7 empty] | Mr. Shahab | Improvements
[7 empty] | Mr. Shahab | Domain parking
[7 empty] | Mr. Shahab | Test the site Properties
[7 empty] | Mr. Shahab | Test the site
[7 empty] | Mr. Shahab | Upload Content Off-Portal
|  |  |  | BBCWSTBD.ORG | IBM SAS Server | Enhancement of the site | Mr. Shahab | Signed Contract
[7 empty] | Mr. Shahab | Domain authority transfer
[5 empty] | Win2k3 OS |  | Mr. Shahab | Existing domain to park in BBC Loca Domain
Mr. Shahab
[7 empty] | Mr. Shahab | Test the site
[7 empty] | Mr. Shahab | Upload Content at the site
|  |  |  | BBCWSTBD |  | Central Printing, Print Server | Mr. Shahab | Signed Contract
[7 empty] | Mr. Shahab | Develop the site
[5 empty] | Network Printer |  | Mr. Shahab | Test the site
[7 empty] | Mr. Shahab | Domain Registration options
[5 empty] | Print Server |  | Mr. Shahab
Mr. Shahab
|  |  |  | BOL SLA |  | Contract Review | Mr. Shahab | Contract Review
[6 empty] | Options | Mr. Shahab
Mr. Shahab
Mr. Shahab
|  |  |  | BBCWSTBD |  | WiFi Security and Expansion | Mr. Shahab | Finalize contents
Mr. Shahab
[7 empty] | Mr. Shahab | Test the site
Mr. Shahab
|  | E-Mail Hosting | In-House | BBCWSTBD | Exchange 2k3 or later | Development of the Server Systems | Mr. Shahab | Real IP Assignment
[7 empty] | Mr. Shahab | Domain Parking
[7 empty] | Mr. Shahab | Existing domain to park
[7 empty] | Mr. Shahab | Develop the site
[7 empty] | Mr. Shahab | Test the site
Mr. Shahab
[6 empty] | Development of the Site | Mr. Shahab
[7 empty] | Mr. Shahab | Design onto the template
|  | Active Directory Services | In-House | BBCWSTBD | Identity Management | Readiness for hosting all web sites | Mr. Shahab | Procure the web hosting solution
[5 empty] | Security |  | Mr. Shahab | FTP Server
[5 empty] | WSUS |  | Mr. Shahab | Register for administrataion of domains and park all domains
[5 empty] | DFS | Annual Maintenance of the e-mail site | Mr. Shahab | File Server
[5 empty] | NAP |  | Mr. Shahab | Arrange for disaster recovery options
[5 empty] | Righrts Management |  | Mr. Shahab | Backup
[5 empty] | Disaster Rec. |  | Mr. Shahab
Internet Services | Active Directory Integration |  | In-House | BBCWSTBD | Application Server |  | Mr. Shahab | Bussiness plan execution
[5 empty] | Clustering Server |  | Mr. Shahab | Bussiness plan execution
[5 empty] | File Server |  | Mr. Shahab | Bussiness plan execution
|  |  | In-House | BBCWSTBD | Storage Server | DFS, Shadow Copies of Shared Folders, | Mr. Shahab | Bussiness plan execution
[5 empty] | Management Server |  | Mr. Shahab | Bussiness plan execution
[7 empty] | Mr. Shahab | Bussiness plan execution
|  | Antiviral/Spam Solutions (Kaspersky/McAfee/AVG Corporate Solutions) | In-House | BBCWSTBD |  | Automated Deployment Services, Group Policy Management, | Mr. Shahab | Bussiness plan execution
[7 empty] | Mr. Shahab | Bussiness plan execution
[7 empty] | Mr. Shahab | Bussiness plan execution
|  |  |  | BBCWSTBD |  |  | Mr. Shahab | Bussiness plan execution
[5 empty] | Networking & Access Technologies | System Resource Manager | Mr. Shahab | Bussiness plan execution
[7 empty] | Mr. Shahab | Bussiness plan execution
|  |  |  | BBCWSTBD |  |  | Mr. Shahab | Bussiness plan execution
[6 empty] | DNS | Mr. Shahab | Bussiness plan execution
[6 empty] | IPSec | Mr. Shahab | Bussiness plan execution
| WiFi Services |  | In-House | BBCWSTBD |  | NAP, VPN | Mr. Shahab | Bussiness plan execution
[6 empty] | Wireless Networking | Mr. Shahab | Bussiness plan execution
Mr. Shahab
Mr. Shahab
Mr. Shahab
Mr. Shahab
[5 empty] | Print Servers | Print Services | Mr. Shahab | Bussiness plan execution
[7 empty] | Mr. Shahab | Bussiness plan execution
[5 empty] | Security Services | Kerberos Authentication | Mr. Shahab | Bussiness plan execution
[6 empty] | PKI | Mr. Shahab | Bussiness plan execution
[6 empty] | Network Access Protection | Mr. Shahab | Bussiness plan execution
[6 empty] | Security Configuration | Mr. Shahab | Bussiness plan execution
[5 empty] | Terminal Servers |  | Mr. Shahab | Bussiness plan execution
[5 empty] | Media Servers |  | Mr. Shahab | Bussiness plan execution
[5 empty] | Rights Management Servers |  | Mr. Shahab | Bussiness plan execution
Mr. Shahab
Note on E35: Shuvro: New Businesses are stated in separate file